## ENTERPRISE VIEW
| BID PROCESS | [5 empty] | PURCHASE ORDERS & STARTS |  |  | CONTRACTING | [8 empty] | ESTIMATING CYCLE |  |  | AWARDED JOBS CYCLE |  |  | CARDS & PULL LIST PREPERATION
1 | REQUEST FOR PROPOSAL |  |  |  |  | 1 | CUSTOMER PROVIDES RELEASE DOCS |  | 1 | LETTER OF INTENT RECEIVED
2 | CONSTRUCTION DOCS PROVIDED TO CVC |  |  |  |  | 2 | CVC CREATES START OFF PURCHASE ORDER |  | 2 | ORIGINAL CONTRACT RECEIVED | [8 empty] | CUSTOMER RELEASES DOCUMENTS FOR BID |  |  | PURCHASE ORDER FROM CUSTOMER |  |  | APPROVED PLANS
3 | PLANS, SCOPE OF WORKS, & PERTINENT DOCS DOWNLOADED |  |  |  |  | 3 | ENTER LOT INFORMATION |  | 3 | PRICING SCHEDULE REVIEWED
4 | PROJECT FOLDERS CREATED |  |  |  |  | 4 | APPLY PLANS & OPTION PER LOT |  | 4 | PRICING SCHEDULE REVISIONS | [8 empty] | COPY & CREATE MASTER FOLDER: BUILDER - CITY - PROJECT |  |  | START NOTIFICATION TO CVC OFFICE |  |  | LAYOUT CARD
5 | eTAKEOFF - QUANTITY SURVEY |  |  |  |  | 5 | VERIFY CONTRACT, PROPOSAL MATCH |  | 5 | SCOPE OF WORK REVIEWED
6 | REQUEST FOR CONCRETE MATERIAL QUOTES |  |  |  |  | 6 | VERIFY LATEST BUDGET IN PLACE |  | 6 | SCOPE OF WORK REVISIONS | [8 empty] | DOWNLOAD CUSTOMER DOCS TO FOLDERS |  |  | TEAM NOTES PLANS AND OPTIONS FOR START |  |  | FORMSET CARDS
7 | RFIs & VALUE ENGINEERING CONCEPTS |  |  |  |  | 7 | VERIFY SLAB REPORT MARGIN |  | 7 | INSURANCE REQUIREMENT REVIEW
8 | DESKTOP INTELLIGENCE REVIEW FOR SPEEDS & RATES |  |  |  |  | 8 | UPDATE START TRACKER |  | 8 | INSURANCE REQUIREMENT REVISIONS | [8 empty] | PLAN PREP FOR ETAKEOFF |  |  | START PACKET BUILT WITH PLOT PLANS |  |  | HARDWARE CARDS
9 | FIELD MANAGER REVIEW |  |  |  |  | 9 | JC IMPORT |  | 9 | CUSTOMER FEEDBACK
10 | CVC PROPOSAL REVISIONS | [7 empty] | 10 | NEGOTIATIONS AND REVISIONS | [8 empty] | ETAKEOFF QUANTITY SURVEY |  |  | START PACKET PROVIDED TO ESTIMATING FOR START PROCESS |  |  | PULL LIST CREATION PER PLAN & OPTION | PULL LIST CREATION
11 | PROPOSAL APPROVAL | [7 empty] | 11 | CVC SIGNED CONTRACT
12 | PROPOSAL SENT TO CUSTOMER FOR REVIEW | [7 empty] | 12 | CUSTOMER EXECUTED CONTRACT | [8 empty] | BRIDGE TO SAGE ESTIMATING |  |  | STARTS ENTERS LOT, ADDRESS, PLANS, AND OPTIONS |  |  |  | FORMSET CARDS QTY COUNT
13 | CLIENT PROPOSAL REVISIONS | [7 empty] | 13 | CVC START PRICING UPDATED
14 | NEGOTIATION & SCOPE OF WORK DISCUSSIONS | [7 empty] | 14 | CVC BILLING VERIFICATION | [8 empty] | BUDGETING - DESKTOP INTELLIGENCE REPORTING |  |  | CONTRACT, PROPOSAL, AND START PRICING VERIFIED |  |  |  | HARDWARE CARDS QTY COUNT
15 | AWARD PROCESS | [7 empty] | 15 | JOB/SUBJOB CONTRACT SETTLEMENT
[19 empty] | FIELD MANAGER REVIEW |  |  | JC IMPORT CREATED - COMPILED BUDGET CREATED |  |  |  | APPLY QTY NEEDED TO PULL LIST ORDER FORM FOR PLAN/OPT
QUOTE
[10 empty] | PURCHASE ORDER | [8 empty] | APPROVED BUDGET |  |  | JC IMPORT PROVIDED TO JOB COSTING FOR eCMS |  |  |  | FIELD SUPER REVIEW & APPROVAL
GOODS RECEIPT
| VENDOR/CUSTOMER |  | ESTIMATING/BUDGETS | [6 empty] | 3-WAY MATCH | [8 empty] | BUDGET APPLIED TO START |  | PROJECT MASTER START |  |  |  | PRE-BUILT ORDER QUANTITIES | OFFICE APPLIES QTY PER PLAN TO MASTER START
MATERIAL REQUIRMENT PULL SHEET AKA CVC ORDPROCENT IMPORT
|  |  | STARTS |  | PURCHASE ORDERS |  |  | GOODS RECEIPT FOR MATERIAL |  | INVOICE VERIFICATION | ACCOUNTS PAYABLE |  |  |  |  | BANK | [5 empty] | STARTS
CONTRACTS
[18 empty] | EQUIPMENT | WAREHOUSE PROCESSING & IMPORTS |  |  | SCHEDULING |  |  | CREWS AVAILIBILITY
[8 empty] | YARD L&M STOCKS |  |  |  | ASSET MANAGEMENT
|  |  | MATERIAL REQUIREMENT PULL SHEET | [15 empty] | STAGING OF MATERIAL | PLP - DELTA FROM ORDER TO STAGED IDENTIFIED |  | DELIVERY OF MATERIALS
CASH FLOW
| SALES PLANNING | [6 empty] | GOODS ISSUE | [10 empty] | WAREHOUSE RELEASES ORDER TO SUB JOB | PLP - WAREHOUSE IMPORTS ORDER |  | CREWS AND MATERIAL COSTS MEASURED ON JOB/SUBJOB FOR ACTUALS
|  |  |  | BILL OF MATERIAL | [7 empty] | COST CENTER & JOB COSTING POSTING
| DEMAND MANAGEMENT | [17 empty] | WAREHOUSE STOCK AVAILABILITY APPLIED | PLP - WAREHOUSE ORDER REVISIONS |  | AL MOBILE |  | MATERIAL TRANSFERS
[10 empty] | PROFIT CENTERS |  | PAYROLL | AL MOBILE
[10 empty] | PROJECT & PHASE | [8 empty] | WAREHOUSE CURRENT STOCK LIST CHECKED | PLP - WAREHOUSE & IN-FIELD STOCK AVAILABILITY |  |  |  | TRANSFERS TOTALS APPLIED TO NEXT SUB JOB
[10 empty] | MATERIALS COSTS | [8 empty] | STANDARD STOCKING FOR ITEMS | SUB JOB HAS MATERIAL REQUIREMENTS |  |  | STARTS
[10 empty] | LABOR COSTS | GENERAL LEDGER
|  |  |  | MASTER PLAN SCHEDULE | [5 empty] | EQUIPMENT COSTS | [8 empty] | PURCHASING FOR WAREHOUSE | PRE-BUILT ORDER QUANTITIES PROVIDED
ROUTINGS/AVAILABILITY
MEANS CONNECTED PROCESSES
| PRODUCT COSTS |  |  | CREWS & EQUIPMENT |  |  |  | SCHEDULING
[10 empty] | INSPECTION & CLOSED JOBS |  | ACCOUNTS RECEIVABLE
|  | PURCHASING COST INDEX (GENERAL LEDGER) | [5 empty] | AL MOBILE |  | JOB COST REVIEW |  |  |  | 3-WAY MATCH |  |  | VENDOR/CUSTOMER
[10 empty] | FINAL CLOSING FOR PHASES |  |  |  | PURCHASE ORDERS | ACTUAL BILLING
| PROFITIBILITY ANALYSIS eCMS | [13 empty] | CONTRACTS
|  |  |  | YARD STOCK | [5 empty] | MATERIAL SETTLEMENT | DELIVERY/RETURNS
PRODUCTION ORDER PROCESSING & STRUCTURE
1 | ORDER REQUEST (VENDOR/CUSTOMER) |  |  |  | SUPPLIER QUOTATION
2 | ORDER CREATION (CVC- START)
3 | MATERIAL REQUIREMENT & AVAILABILITY CHECKS |  |  |  | SUPPLIER DELIVERY |  |  | 3-WAY MATCH
4 | EQUIPMENT COMMITMENT
5 | ORDER RELEASE |  |  |  | GOODS RECEIPT
6 | MATERIAL INFO TRANSMITTED TO YARD
7 | MATERIAL STAGING PER PROJECT PHASE |  |  |  | SUPPLIER INVOICE
8 | MATERIAL CONSUMPTION POSTED TO GL
9 | MATERIAL RELEASED TO PROJECT AND PHASE
10 | MATERIAL RETURNED FROM PROJECT AND PHASE |  |  |  | VENDOR PAYMENT |  | ACCOUNTS PAYABLE PROCESS
11 | CONFIRMATION OF RETURNED MATERIAL |  |  |  | 1 | SELECT PAYMENT METHOD AND BANK
12 | WIP DETERMINATION/PHASE CLOSING |  |  |  | 2 | SELECT ITEMS FOR PAYMENT
13 | GOODS RECEIPT FOR GL |  |  |  | 3 | CALCULATE PAYMENT AMOUNTS
14 | ORDER SETTLEMENTS IN JOB COSTING |  |  |  | 4 | POST PAYMENT DOCUMENT
15 | CLOSED PHASE |  |  |  | 5 | ARCHIVE PAYMENT DOCUMENT
Note on D23: Scott MacFarlane: SEE EXPANDED VIEW ON RIGHT SIDE OF XL

## SNOWMAN VIEW
BUDGET FROM ESTIMATE
SCHEDULING
|  |  | NEGOTIATION |  | AWARD PROCESS
QUOTE & BUDGET
YARD FOR MATERIALS
[7 empty] | PULL LISTS |  |  |  |  | EQUIPMENT NEEDS
[7 empty] | MRP | START
BID INVITE & REWQUEST FOR PROPOSAL | [12 empty] | CREW ASSIGNMENTS
PURCHASE ORDERS w PLANS & OPTIONS
NEW/VENDOR CUSTOMER | [13 empty] | PURCHASE REQUISITIONS
MATERIAL PURCHASING
SALES CYCLE
GOODS RECEIPT
PRODUCTION CYCLE
3-WAY
PROCUREMENT CYCLE
INVOICING
LIEN RELEASE
ACCOUNTS RECEIVABLE BILLING
|  |  | RECEIPT OF PAYMENTS/CLOSED JOB |  |  | PROJECT COMPLETION | [12 empty] | PAYMENT TO SUPPLIER
CONSTRUCTION & WORK
JOB COST L&M w EQUIPMENT
COSTS ASSIGNED TO COST CENTER/PROJECT/PRODUCTION
INSPECTION & CONFIRMATION OF COMPLETION
MATERIAL DELIVERED/RELEASED TO COST CENTER/PROJECT/PRODUCTION
QUALITY CONTROL

## MASTER DATA
PURCHASING ORGANIZATION |  |  |  | CLIENT |  |  |  | EMPLOYEE GROUP
|  |  |  | OPERATING CONCERN |  |  |  | SUB GROUP
|  |  |  | CONTROLLING AREA |  | COST CENTER |  | PAYROLL
PERSONNEL AREA
PERSONNEL SUBAREA
| CHART OF ACCOUNTS |  |  | COMPANY CODE |  | CREDIT CONTROLLING
[5 empty] | FISCAL YEAR VARIANT |  |  |  |  | ORGANIZATION UNIT
SALES ORANIZATION
|  | BUSINESS AREA | [7 empty] | JOB
DISTRIBUTION CHANNEL
POSITION
DIVISION
PERSON
|  |  |  | PROJECT/PLANT |  | SALES AREA
WAREHOUSE MANAGEMENT
MAINTENANCE PLANNING PLANT | MAINTENANCE PLANT

## START PROCESS
| ESTIMATING CYCLE |  | AWARDED JOBS CYCLE | CARDS & PULL LIST PREPERATION
| CUSTOMER RELEASES DOCUMENTS FOR BID |  | PURCHASE ORDER FROM CUSTOMER | APPROVED PLANS
| COPY & CREATE MASTER FOLDER: BUILDER - CITY - PROJECT |  | START NOTIFICATION TO CVC OFFICE | LAYOUT CARD
| DOWNLOAD CUSTOMER DOCS TO FOLDERS |  | TEAM NOTES PLANS AND OPTIONS FOR START | FORMSET CARDS
| PLAN PREP FOR ETAKEOFF |  | START PACKET BUILT WITH PLOT PLANS | HARDWARE CARDS
| ETAKEOFF QUANTITY SURVEY |  | START PACKET PROVIDED TO ESTIMATING FOR START PROCESS | PULL LIST CREATION PER PLAN & OPTION | PULL LIST CREATION
| BRIDGE TO SAGE ESTIMATING |  | STARTS ENTERS LOT, ADDRESS, PLANS, AND OPTIONS |  | FORMSET CARDS QTY COUNT
| BUDGETING - DESKTOP INTELLIGENCE REPORTING |  | CONTRACT, PROPOSAL, AND START PRICING VERIFIED |  | HARDWARE CARDS QTY COUNT
| FIELD MANAGER REVIEW |  | JC IMPORT CREATED - COMPILED BUDGET CREATED |  | APPLY QTY NEEDED TO PULL LIST ORDER FORM FOR PLAN/OPT
| APPROVED BUDGET |  | JC IMPORT PROVIDED TO JOB COSTING FOR eCMS |  | FIELD SUPER REVIEW & APPROVAL
| APPROVED SAGE BUDGET | PROJECT MASTER START |  | ORDER QUANTITIES | OFFICE APPLIES QTY PER PLAN TO MASTER START
MATERIAL REQUIRMENT PULL SHEET
BILL OF MATERIAL
EQUIPMENT | WAREHOUSE |  | SCHEDULING | CREWS
| PURCHASING |  | AL MOBILE
JOB/SUBJOB